## Project Planner
NR Podcast Episode Production Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | 2025-02-16 |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | TARGET COMPLETION | PLAN DURATION | ACTUAL START | DATE COMPLETED | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2024-11-01 to 2026-01-01
Ep00: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 25%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep01: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep02: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep03: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep04: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep05: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Planning & drafting | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Writing & editing | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Recording & post-editing | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Show notes & clips | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Final touches & posting | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Audience engagement | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep06: | 2024-11-18 |  | 1 |  |  |  | 0%
Planning & drafting | 2024-11-12 | 2024-11-24 | 5 |  |  |  | 0%
Writing & editing | 2025-02-16 |  | 8 |  |  |  | 0%
Recording & post-editing | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Show notes & clips | 2025-03-09 | 2025-03-16 | 4 |  |  |  | 0%
Final touches & posting | 2025-03-16 | 2025-03-23 | 5 |  |  |  | 0%
Audience engagement | 2025-03-23 | 2025-03-30 | 7 |  |  |  | 0%
Formulas:
PLAN START = [PLAN START, row below]
PLAN START = [PLAN START, row above]+1
TARGET COMPLETION = [PLAN START]+7
ACTUAL START = [PLAN START]+1
ACTUAL START = [PLAN START]
DATE COMPLETED = [TARGET COMPLETION]

## Project Planner (2)
NR Podcast listener community planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | 2025-02-16 |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | TARGET COMPLETION | PLAN DURATION | ACTUAL START | DATE COMPLETED | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2024-11-01 to 2026-01-01
Ep00: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep01: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep02: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep03: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep04: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep05: | 2024-11-11 | 2025-03-09 | 118 | 2024-11-11 |  | 97 | 25%
Engage audience | 2024-11-11 | 2024-11-23 | 12 | 2024-11-12 | 2024-11-23 | 11 | 100%
Ask to subscribe for free | 2024-11-12 | 2024-11-24 | 12 | 2024-11-12 | 2024-11-24 | 12 | 100%
Incentivize paid subscriptions | 2025-02-16 | 2025-02-22 | 6 |  |  |  | 10%
Invite patrons into roles | 2025-02-23 | 2025-03-02 | 7 |  |  |  | 0%
Onboard patron roles | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Nurture community | 2025-03-09 | 2025-03-16 | 7 |  |  |  | 0%
Ep06: | 2024-11-18 |  | 1 |  |  |  | 0%
Engage audience | 2024-11-12 | 2024-11-24 | 5 |  |  |  | 0%
Ask to subscribe for free | 2025-02-16 |  | 8 |  |  |  | 0%
Incentivize paid subscriptions | 2025-03-02 | 2025-03-09 | 7 |  |  |  | 0%
Invite patrons into roles | 2025-03-09 | 2025-03-16 | 4 |  |  |  | 0%
Onboard patron roles | 2025-03-16 | 2025-03-23 | 5 |  |  |  | 0%
Nurture community | 2025-03-23 | 2025-03-30 | 7 |  |  |  | 0%
Formulas:
PLAN START = [PLAN START, row below]
PLAN START = [PLAN START, row above]+1
TARGET COMPLETION = [PLAN START]+7
ACTUAL START = [PLAN START]+1
ACTUAL START = [PLAN START]
DATE COMPLETED = [TARGET COMPLETION]
Engage audience - reply to comments
Attract interest - invite sub as a follower
Incentivize investment - supporter
Identify innovators - patrons
Onboard innovators - roles
Build community - PNR [AMA sessions]
Engage audience
Incentivize to subscribe
Incentivize supporters
Invite patros into roles
Onboard patron roles
Nurture community

## Calendar
| Year | 2025 |  |  |  |  | Month | 1 | [5 empty] | Start Day | 44 |  |  | 1:Sun, 2:Mon …
2025 | [10 empty] | Year-at-a-glance
2025-01-01 | [7 empty] | 2025-02-01 | [7 empty] | 2025-03-01 | [6 empty] | 2025-04-01
M | T | W | T | F | S | S |  | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | [6 empty] | 2025-02-01 | 2025-02-02 | [6 empty] | 2025-03-01 | 2025-03-02 |  | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06
2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 |  | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 |  | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13
2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 |  | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 |  | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20
2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 |  | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 |  | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27
2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 |  |  |  | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 |  |  |  | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-04-28 | 2025-04-29 | 2025-04-30
2025-03-31
2025-05-01 | [7 empty] | 2025-06-01 | [7 empty] | 2025-07-01 | [6 empty] | 2025-08-01
M | T | W | T | F | S | S |  | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | [7 empty] | 2025-06-01 |  |  | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 |  |  |  |  | 2025-08-01 | 2025-08-02 | 2025-08-03
2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 |  | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 |  | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10
2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 |  | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 |  | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17
2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 |  | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 |  | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24
2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 |  |  | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 |  | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 |  |  |  | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
2025-06-30
2025-09-01 | [7 empty] | 2025-10-01 | [7 empty] | 2025-11-01 | [6 empty] | 2025-12-01
M | T | W | T | F | S | S |  | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S
2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 |  |  |  | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | [6 empty] | 2025-11-01 | 2025-11-02 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07
2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 |  | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 |  | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14
2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 |  | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 |  | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21
2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 |  | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 |  | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28
2025-09-29 | 2025-09-30 | [6 empty] | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 |  |  |  | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-29 | 2025-12-30 | 2025-12-31

## notes
2025-02-16
2025-04-30
73
10.4286
Podcast production steps
Planning & drafting
Writing & editing
Recording & post-editing
Show notes & details
Final touches & posting